## Pricing Summary
Customer Pricing Calculator
Project Name | Paytm-like Application
Currency | INR
Target Gross Margin | 25%
Overhead % | 10%
Contingency % | 0.15
Metric | Minimum | Likely / PERT | Maximum | Notes
Labor Cost | 60000 | 78750 | 112500 | Based on three-point effort
Vendor / Other Costs | 0 | 0 | 0 | Enter on WBS line items
Subtotal Direct Cost | 60000 | 78750 | 112500
Overhead | 6000 | 7875 | 11250
Contingency | 9900 | 12993.75 | 18562.5
Total Cost Basis | 75900 | 99618.75 | 142312.5
Customer Price @ Target Margin | 101200 | 132825 | 189750
Recommended Commercial Range | 101200 | 132825 | 189750
Commercial Lever | Value | Formula / Guidance
Target Margin | 25% | Gross margin target
Minimum Acceptable Margin | 18% | Set your walk-away threshold
Discount % from Target | 5% | Negotiation allowance
Indicative Negotiation Price | 126183.75 | Target price less negotiation discount
Floor Price | 121486.2805 | Likely cost basis priced at minimum margin
Pricing Model | Recommended Use | Customer Charging Method
Fixed Price | Stable, well-defined scope | Milestone / fixed contract
Time & Material | Evolving requirements | Hours/days × agreed rate
Hybrid | Discovery + uncertain build | Fixed phases + T&M changes
Managed Service | Post-go-live | Monthly recurring fee
How to use
1. Update Resource Rates with your company's fully loaded monthly costs.
2. Break the customer requirement into WBS items on the WBS Estimate tab.
3. Enter optimistic, most-likely and pessimistic hours for each item.
4. Add vendor/third-party costs directly to the WBS.
5. Set target margin, overhead and contingency on Pricing Summary.
6. Use Minimum / Likely / Maximum customer price as your commercial range.
7. Use Change Request for scope changes after contract signature.

## Resource Rates
Resource Rate Card
Role | Monthly Loaded Cost (INR) | Productive Hours/Month | Hourly Cost (INR) | Daily Cost (INR) | Notes | Active?
Business Analyst | 150000 | 120 | 1250 | 10000 | Example rate | Yes
UI/UX Designer | 180000 | 120 | 1500 | 12000 | Example rate | Yes
Developer | 200000 | 120 | 1666.6667 | 13333.3333 | Example rate | Yes
Senior Developer | 300000 | 120 | 2500 | 20000 | Example rate | Yes
Architect | 450000 | 120 | 3750 | 30000 | Example rate | Yes
QA Engineer | 150000 | 120 | 1250 | 10000 | Example rate | Yes
DevOps/SRE | 250000 | 120 | 2083.3333 | 16666.6667 | Example rate | Yes
Project Manager | 300000 | 120 | 2500 | 20000 | Example rate | Yes
Security Engineer | 300000 | 120 | 2500 | 20000 | Example rate | Yes

## WBS Estimate
WBS / Three-Point Effort Estimate
WBS ID | Phase | Feature / Task | Role | Optimistic Hrs | Most Likely Hrs | Pessimistic Hrs | PERT Expected Hrs | Hourly Cost | Labor Cost | Vendor/Other Cost | Total Cost | Confidence | Assumptions / Dependencies | Min Cost | Likely Cost | Max Cost | Cost Quoted | Actual Hours | Variance Hours | Actual Cost | Profit | Status
1.1 | Discovery | MVP Requirements & analysis | Business Analyst | 48 | 60 | 90 | 63 | 1250 | 78750 |  | 78750 | 90% | MVP scope remains controlled; one primary decision-maker available; timely stakeholder feedback; existing documentation provided; analysis excludes detailed UI/UX and coding; architecture only to MVP estimation level; integrations assessed from available documentation; compliance discovery only, not legal consulting. | 60000 | 78750 | 112500 | 112500 | 63 | 0 | 78750 | 33750 | Complete
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Change Request
Change Request Pricing Calculator
CR ID | Change Description | Role | Hours | Hourly Cost | Labor Cost | Other Cost | Contingency % | Customer Price
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%
|  |  |  | 0 |  |  | 15%

## Assumptions
Estimation Assumptions & Risks
Category | Assumption / Dependency | Impact if Wrong | Cost Impact | Owner | Notes
Scope | MVP vs full fintech scope must be confirmed | High | TBD | BA | Define in discovery
Integrations | Payment/KYC APIs available and documented | High | TBD | Architect | Vendor/API dependency
Compliance | Customer provides required regulatory/compliance requirements | High | TBD | Customer | Validate before fixed price
Security | Pen-test and security requirements are known | Medium | TBD | Security | Allow for remediation
Scale | Peak transaction/user volumes are known | High | TBD | Architect | Affects cloud architecture